ScouterZero Marketing Strategy & Intern Playbook

Version 1.0  |  Team: Aniket + 3 Interns

1. What We Are Building & Why

ScouterZero helps Product Managers find curated startup jobs. Our marketing goal is to acquire users organically through content, community, and automation — with zero paid spend.

Long-term vision: Build a repeatable, automated content pipeline that scales across future products.

2. North Star Metric & Acquisition Funnel

North Star Metric: Registered users on ScouterZero

Funnel (track each stage weekly)

Instagram Views

Instagram Followers

Website Visits

Email Sign-ups / Registrations

Repeat Visitors

Paying Customers

3. OKRs — Month 1 & Month 2

Objective 1: Build Instagram Presence

KR1: 1,000 followers by end of Month 1

KR2: 50,000 total reel views by end of Month 1

Objective 2: Drive Website Traffic

KR1: 500 unique weekly visitors by end of Month 2

KR2: 3 influencer shoutouts secured by end of Month 2

Objective 3: Convert Visitors to Users

KR1: 200 email registrations by end of Month 2

KR2: Email-to-registration conversion rate > 40%

Objective 4: Build Scalable Content Pipeline

KR1: Automated content workflow live by Week 3

KR2: 20+ posts/week producible with < 5 hours of human effort

4. Target Audience

Primary

Product Managers actively job hunting in UAE, Singapore, UK, US, Europe (0–5 years experience, startup/scale-up roles).

Core pain: Job search is scattered, hidden roles are hard to find, no signal on culture fit.

Secondary

Career switchers targeting PM roles.

Where They Live Online

Instagram: career content creators

LinkedIn: professional credibility, job posts

WhatsApp / Discord: ProductTank chapters, PM communities

Reddit: r/ProductManagement, r/cscareerquestions

Reference Creators to Study

@decodewithavyay  |  @anshu_career_hacks  |  @vin_thejobhunt  |  @kaamkibaatein_

5. Content Strategy

Framework: Hook → Content → CTA

Every piece of content must follow this structure:

Hook: Stop the scroll in 0–3 seconds. Lead with tension or a bold claim.

Content: Deliver genuine value — tips, market insight, product demo, or data.

CTA: Drive one action: "Link in bio to apply" / "Comment JOBS and I'll DM you the list."

Content Mix (80/20 Rule)

80% — Value content: job search tips, PM interview prep, market data, career advice

20% — Product content: ScouterZero features, specific job listings, recruiter reveals

Content Types

Instagram Reels / LinkedIn Video: Speaker-to-camera: personal story, job tip, market insight (15–45 sec)

Screen recording of ScouterZero in action

Text-on-screen: fast-paced stats or tips (low production cost)

Carousels: Problem → Insight → Solution → Proof → CTA  |  7–10 slides max, large text, minimal clutter

LinkedIn Text Posts: Personal narrative + data point + opinion  |  Posted by Aniket (founder voice)

Weekly Content Calendar

| Day | Format | Platform | Owner |
| --- | --- | --- | --- |
| Monday | Carousel | Instagram + LinkedIn | Intern 1 |
| Tuesday | Reel | Instagram | Intern 1 |
| Wednesday | LinkedIn Post | LinkedIn | Aniket |
| Thursday | Reel | Instagram | Intern 1 |
| Friday | Carousel | LinkedIn | Intern 1 |
| Saturday | Community Post | Reddit / Discord | Intern 2 |
| Sunday | Plan + Review | All channels | Full team |

6. Distribution & Outreach

Channel Priority

Instagram — Primary brand-building channel

LinkedIn — Credibility + direct recruiter/PM audience

WhatsApp + Discord groups — Direct, high-intent user acquisition

Reddit — Organic discovery, longer shelf life

Glassdoor / ProductTank — Niche placement

Community Outreach Playbook  (Intern 2 owns)

Week 1 — Research & Join: Find and join 10 WhatsApp PM groups in UAE, UK, US, Singapore

Join 5 Discord servers (ProductTank chapters, PM communities)

Join 3 Reddit communities — read norms before posting

Week 2+ — Contribute then Convert: Give value 4× before mentioning ScouterZero. Share job leads, tips, answer questions first.

Influencer Outreach  (Intern 2 + Aniket)

Target 10 micro-influencers (10k–100k followers) in PM/career niche in UAE, Singapore, UK, US

Outreach message: "Hey [Name], love how you break down [topic]. We built a tool your audience would find useful — ScouterZero curates hidden startup PM jobs in [their region]. Would love to give you free access. No obligation to post — just want your honest take."

Tracking sheet columns: Name | Followers | Region | Status | Response | Outcome

7. Automation & Technical Setup

Goal: Reduce manual effort so 4 people can produce like a 10-person team.

Priority Automations  (Intern 3 owns)

Phase 1 (Weeks 1–2): Auto-schedule posts to Instagram + LinkedIn via N8N

Build content calendar tracker in Google Sheets

Phase 2 (Weeks 3–4): Reddit/community monitoring — flag posts where ScouterZero adds value

Auto-generate first-draft video scripts using Claude (Hook + Content + CTA)

Phase 3 (Month 2): Influencer DM automation (first-touch only; human follows up)

Weekly metrics pull: Instagram + GA4 → Google Sheets dashboard

Tools Stack

N8N — workflow automation

Higgsfield — AI video generation ($99/month; evaluate after free trial)

Claude Code — content drafting + script generation

Google Sheets — content calendar, influencer tracker, metrics dashboard

GA4 + Microsoft Clarity — website analytics (already live)

8. Team Ownership

| Initiative | Aniket | Intern 1 | Intern 2 | Intern 3 |
| --- | --- | --- | --- | --- |
| Strategy & OKRs | A/R | – | – | – |
| Video scripts & calendar | A/C | R | – | – |
| Carousel + post creation | C | R | – | – |
| LinkedIn posts (founder) | R | – | – | – |
| Community outreach | A | – | R | – |
| Influencer partnerships | A/C | – | R | – |
| N8N automation build | A | – | – | R |
| Analytics & reporting | A | C | C | R |

R = Responsible (does the work)   |   A = Accountable (owns outcome)   |   C = Consulted

Intern Profiles

Intern 1 — Content Creator: All video and carousel production. Output: 5 posts/week. Tools: Higgsfield, Canva, Claude.

Intern 2 — Community & Outreach: Community infiltration + influencer pipeline. Output: 10 communities joined, 5 influencer conversations active/week.

Intern 3 — Technical & Automation: N8N workflows + analytics dashboard. Output: Automated pipeline live by Week 3, weekly metrics report.

9. Week 1 Setup Checklist

All Interns (Days 1–2)

☐  Get Claude Code access — check GitHub Student Program first

☐  Complete Excel basics: VLOOKUP, XLOOKUP, Pivot Tables, Conditional Formatting

☐  Complete N8N intro course

☐  Set up Google Docs / Sheets collaboration

Intern 1 — Content

☐  Study 20 reels from reference creators — note hooks, formats, CTAs

☐  Create Higgsfield trial account

☐  Draft first 5 content ideas using Hook-Content-CTA framework

☐  Produce 1 sample reel + 1 sample carousel for review

Intern 2 — Community

☐  Build influencer tracker spreadsheet (Name, Followers, Region, Contact, Status)

☐  Identify and list 20 target influencers

☐  Find and list 15 WhatsApp/Discord/Reddit communities to join

☐  Draft community outreach message template

Intern 3 — Technical

☐  Set up N8N (cloud trial)

☐  Build Google Sheets content calendar template

☐  Connect GA4 to a basic metrics dashboard

☐  Map out first automation: content scheduling flow

10. KPIs & Weekly Reporting

| Metric | Week 4 Target | Week 8 Target |
| --- | --- | --- |
| Instagram followers | 500 | 2,000 |
| Instagram reach / week | 20,000 | 75,000 |
| Website unique visits / week | 200 | 1,000 |
| Email registrations (total) | 50 | 250 |
| Communities active in | 10 | 25 |
| Influencer conversations active | 5 | 15 |
| Influencer posts secured | 1 | 5 |

Reporting Cadence

Every intern fills in metrics by Sunday evening

Intern 3 compiles into the shared Google Sheets dashboard

Monday sync (30 min): review last week + plan this week

11. Working Rhythm

Daily: Each intern posts a 2-line async update daily: "Done / Blocked / Next"

Weekly (Monday, 30 min): Metrics review vs. targets | Blockers cleared | This week's priorities confirmed

Monthly: OKR check-in — what's working, what to kill, what to double down on

Appendix: Ideas Parking Lot (Evaluate Later)

Product Features (Out of Current Scope)

Email newsletter

Job save + filters

CV upload + prep

LinkedIn/email automation for job seekers

Mobile app (iOS/Android)

Recommendation engine

Marketing Tactics for Month 3+

AB testing landing page copy (find free-tier platform first)

Promotional video for ScouterZero (study "One Sec" app launch as reference)

LinkedIn engagement automation with human review layer (N8N + Claude)

SMS outreach (check legal requirements per geography first)